## READ ME FIRST
Protected Utility blueprint
Introduction
Document purpose: | The purpose of this document is to capture all the benefits the agency expects to achieve as a result of transitioning to the blueprint. The identification, articulation and regular tracking and measurement of benefits will enable agencies to: - realise the desired transition benefits, - provide targeted communications to their stakeholder to build awareness and (positively) influence adoption of the change, - provide any early warning of potential problems with the blueprint transition, and - provide a formal tracking mechanism for the identified benefits.
Intended audience: | The intended audience for this document is the agency team members responsible for implementing the blueprint services. This may include: - Agency blueprint project lead and other team members - Agency blueprint change team - Agency blueprint communications and engagement team.
Benefit categories | Below are commonly used benefit categories as well as examples against each category:

## Benefits Assessment
Protected Utility blueprint
Benefits Details | [7 empty] | Benefits Measurement
Benefit ID | Benefit title | Benefit Description | Owner | Link to project objective | Benefit Category | Realisation start date | Realisation end date | Key Performance Indicators (KPIs) | Measurement Description [How will the benefit be measured?] | Beneficiaries (Agency end users / Teams / Functional areas) | Baseline Measure Description [Description of current state] | Target Measure Description [Description of target state]
B1 | Significant increase in functionality and capabilities of the collaboration platform | The MO365 collaboration platform (MS Teams) will include contemporary technical capabilities that will enhance real-time collaboration, enable easier sharing of information as well as improve ability to host virtual meetings. | Agency IT team |  | Non-financial | Capability 'go-live' | Ongoing - expected to endure until tool decommissioning | User Logins | We aim to have at least 90% of our agency user base login once in the first 4 weeks from launch.
B2
B3
B4
B5
B6
B7
B8
B9
B10